## Sheet1
Order | % Complete | Task Name | Ref | Agree? | Notes
1 | 59% | RIC SharePoint site Iteration 1 | US812874
2 | 0% | Develop Questions for Customers | TA1618911 |  | What are the constraints in Germany if we work with CDSID from a centralized SharePoint?
3 | 100% | Build MS Access Prototype | TA1620537 |  | As an MS Access Client with a SharePoint List Server I want to provide a prototype system utilizing a single form with two tab objects (one for the Idea Submission and one for Registration)
4 | 100% | Create home page | US860531 |  | As a development team member I want to see the value added steps as a home page to the Internal SharePoint site so that a constant reminder exists so that select users can select entities from slide that will work as buttons activating that page after sel
5 | 100% | Clone slide 7 | TA1603235 |  | Convert all power point objects to png pictures and add them to a layout of header, 3 columns, and a footer. Out of scope for this task is any formatting is needed that requires SharePoint Designer
6 | 100% | Replace SUPPLIER AND PRESENTER buttons with SUBMIT IDEA button | TA1626718 |  | Find the presentaion slide with these buttons, edit one of them to Submit Idea, create a picture from it, check out the home page, edit it removing the supplier and presenter buttons then add the Submit idea button
7 | 0% | Supplier Information Security | US858885 |  | As a Supplier preparing to register for the IDTE I want to ensure no other Suppliers can see my innovation so that I have time to finish my patent process.
8 | 100% | Event notifications will be different between internal and external Ford Suppliers | US861020 |  | As the product manager I need to ensure that two different email messages are sent to Suppliers. One standard communication to the Suppliers outside of Ford and another external to Ford. The email bodies need to be different.
9 | 100% | Create Prototype VBA code to send Event Notification Messages | TA1618365 |  | As VBA code residing in an Access database triggered by the Event Notification Button click I need to loop through the records in the SUPPLIER_MESSAGE_BODIES inner joined to SUPPLIER_EMAIL on SUPPLIER_TYPE so that the standard message by supplier type wil
10 | 0% | One Waiver per registration | US858902 |  | As a Supplier who has already registered, I want to ensure that I do not have to complete the disclosure form again so that I can reduce my efforts while scanning to see if my dates have been accepted
11 | 0% | Waiver with Ideas | US858820 |  | As a Supplier I need to respond to the Event Notification accepting the waiver and providing a description of each of my ideas so that I can get a chance to present these ideas to Ford.
12 | 0% | Presenters need to be able to update Registered ideas | US858923 |  | As a Supplier who has already registered I want to ensure that I can update the details so that the Supplier I have has the best chance of getting selected to attend this event.
13 | 0% | Disable Registration Button after Receiving Ideas | US865367 |  | As a user I want a reminder that someone representing the company I work at has already registered so that I know where in the process we are
14 | 0% | Notification of Presentation Space Availability | US858841 |  | As an Evalutor I need to notify Suppliers of Idea Presentation Acceptance and provide them with a Mechanism so that Presenters can schedule Presentation time with Ford
15 | 0% | Presenters schedule time with Ford | US858844 |  | As a presenter I want to inform Ford which presentation times work best so that I know when and where to attend the event.
16 | 0% | The Evaluation Team validates Presenter Schedule | US858848 |  | As an Evaluator I need to ensure there are no schedule conflicts between Suppliers so that I can intervene with Suppliers to work out the schedule issues.
17 | 0% | The Evaluation Team helps Presenters to their spaces | US858854 |  | As an Evaluator I need to help presenters get to their space so that they can effectively present their ideas to Ford.