## USER_STORY_SUMMARIES
Formatted ID | Name | Release | Iteration | Schedule State | Plan Estimate | Task Estimate Total | Task Remaining Total | Project | Owner
US812874 | RIC SharePoint site |  | 2019_ITR_IDTE1 | Accepted | 80 | 67 | 37 | ALPHA BRAINS | Venugopal Kodali
US858841 | Notification of Presentation Space Availability |  | 2019_ITR_IDTE1 | Accepted | 10 | 6 | 4 | ALPHA BRAINS | Venugopal Kodali
US858844 | Invitees schedule time with Ford |  | 2019_ITR_IDTE1 | Accepted | 6 | 6 | 4 | ALPHA BRAINS | Venugopal Kodali
US873489 | Manage and Control Product |  | 2019_ITR_IDTE1 | Accepted | 3 | 3 | 0 | ALPHA BRAINS | Bob Rose
US858820 | Notice of Disclaimer Page |  | 2019_ITR_IDTE2 | In-Progress | 5 | 3 | 2 | ALPHA BRAINS | Venugopal Kodali
US858848 | The Evaluation Team validates Presenter Schedule |  | 2019_ITR_IDTE2 | Completed | 5 | 5 | 0 | ALPHA BRAINS | Venugopal Kodali
US858854 | The Evaluation Team helps Presenters to their spaces |  | 2019_ITR_IDTE2 | Defined | 5 | 5 | 5 | ALPHA BRAINS | Venugopal Kodali
US858879 | Supplier hardware and software |  | 2019_ITR_IDTE2 | Defined | 5 | 5 | 5 | ALPHA BRAINS | Venugopal Kodali
US858885 | Supplier Information Security |  | 2019_ITR_IDTE2 | In-Progress | 5 | 5 | 5 | ALPHA BRAINS | Venugopal Kodali
US858902 | One Waiver per registration |  | 2019_ITR_IDTE2 | In-Progress | 2 | 2 | 2 | ALPHA BRAINS | Venugopal Kodali
US858923 | Invitees need to be able to update Registered ideas |  | 2019_ITR_IDTE2 | In-Progress | 5 | 5 | 5 | ALPHA BRAINS | Venugopal Kodali
US858925 | Life cycle of product needs to be at least one year |  | 2019_ITR_IDTE2 | Defined | 5 | 5 | 5 | ALPHA BRAINS | Venugopal Kodali
US860531 | Create home page |  | 2019_ITR_IDTE2 | In-Progress | 16 | 16 | 7 | ALPHA BRAINS | Venugopal Kodali
US861020 | Event notifications will be different between internal and external Ford Suppliers |  | 2019_ITR_IDTE2 | In-Progress | 5 | 5 | 0 | ALPHA BRAINS | Venugopal Kodali
US865367 | Disable Idea Submission Button before Registration |  | 2019_ITR_IDTE2 | In-Progress | 3 | 3 | 0 | ALPHA BRAINS | Venugopal Kodali
US867742 | The Evaluation Team scans bar code to find user information |  | 2019_ITR_IDTE2 | Defined | 5 | 5 | 5 | ALPHA BRAINS | Venugopal Kodali
US898164 | Re-direct Page |  | 2019_ITR_IDTE2 | In-Progress | 60 | 50 | 50 | ALPHA BRAINS | Venugopal Kodali
US898181 | Where is concept being shipped from? |  | 2019_ITR_IDTE2 | In-Progress | 10 | 5 | 5 | ALPHA BRAINS | Venugopal Kodali
US898208 | Ford Idea Submission Page |  | 2019_ITR_IDTE2 | In-Progress | 20 | 10 | 5 | ALPHA BRAINS | Venugopal Kodali
US898214 | Non Ford Idea Submission Page |  | 2019_ITR_IDTE2 | In-Progress | 10 | 7 | 2 | ALPHA BRAINS | Venugopal Kodali
US898351 | Get Team SharePoint Designer access |  | 2019_ITR_IDTE2 | Defined | 20 | 20 | 20 | ALPHA BRAINS | Venugopal Kodali
US898368 | External SharePoint list needs workflow templates from internal site |  | 2019_ITR_IDTE2 | In-Progress | 2 | 2 | 2 | ALPHA BRAINS | Venugopal Kodali
US898533 | Manage and Control Product |  | 2019_ITR_IDTE2 | In-Progress | 3 | 44 | 44 | ALPHA BRAINS | Bob Rose
US901559 | Imperative Strategy |  |  | In-Progress | 5 | 6 | 5 | ALPHA BRAINS